## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Project schedule
| ELEC5550 PROJECT | [5 empty] | Project start: | [7 empty] | 2025-07-21
| Group 0-16 | [5 empty] | Display week: | [7 empty] | 1
[7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Study Break | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-07-21 to 2025-10-19
 | time axis 2025-07-21 to 2025-10-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Initial Project Studies | Everyone | 100% | 2025-07-21 | 2025-07-30 | 10
| Define Goals & Requirements Analysis | Everyone | 100% | 2025-07-21 | 2025-08-17 | 28
| Feasibility and Component Studies | Everyone | 100% | 2025-07-31 | 2025-08-10 | 11
| Risk Assessment | Everyone | 100% | 2025-08-04 | 2025-08-10 | 7
Planning and design
| Individual component study | Everyone | 100% | 2025-08-04 | 2025-08-17 | 14
| Ordering Components | Everyone | 100% | 2025-08-11 | 2025-08-17 | 7
| Individual component Design | Everyone | 100% | 2025-08-11 | 2025-08-24 | 14
| Design Review 1 | Everyone | 100% | 2025-08-18 | 2025-08-31 | 14
Execution
| Individual Component Assembly | Everyone | 100% | 2025-08-25 | 2025-09-07 | 14
| Individual component testing | Everyone | 100% | 2025-08-25 | 2025-09-07 | 14
| System Assembly and Integration | Everyone | 100% | 2025-09-07 | 2025-09-20 | 14
| System protoyping and testing | Everyone | 100% | 2025-09-07 | 2025-09-20 | 14
| Design Review 2 | Everyone | 100% | 2025-09-15 | 2025-09-28 | 14
Evaluation
| System Evaluation and Finalisation |  | 100% | 2025-09-29 | 2025-10-19 | 21
| Documentation and Github Submission |  | 100% | 2025-10-06 | 2025-10-19 | 14
| Final Report and Project submission |  | 100% | 2025-10-06 | 2025-10-20 | 15
| Prepare for Demonstration and Interview |  | 90.91% | 2025-10-06 | 2025-10-28 | 23